## sheet
Stakeholder | Primary/Secondary | Stakeholder concerns regarding project aims and objectives | Notes
ERG System Administrator | Primary | Select Potential Unauthorised Changes to the existing network configurations resulting in the network being inaccessible. The project may be perceived to create more work for the system administrator, they may not have time or the inclination to want to assist. | No Changes will be made to the existing network without prior scheduling and a recovery plan. A project 'buy in' from the system administrator is essential, an effort should be made to endure as limited demand on the existing organisations personnel as practical.
Cyber Security Consultant | Primary | Select Potential lack of assistance from the client in regard to network access or policy and procedural uncertainty. Potential scope misunderstanding. | Initial meetings to capture persons in charge and responsibilities from individuals and the organisation. The scope is to be clearly detailed and agreed in writing with the client organisation.
Directors of the Client Company | Primary | Select Interruption to business operations. Potential exposure of private or confidential data when allowing a third party system privileges. | The project will be engineered to be undertaken without business interruption other than programmed meetings and authorised pre-programmed network alterations. A confidentiality agreement will be signed prior to any information or access being provided to the network or organisational policies or procedures.
Employee/Contractor 'End Users' at ERG | Secondary | Select Potential finding of unauthorised data or applications on organisation owned machines. Feeling threatened by potential change and feeling undertrained to handle the change. | Any unauthorised data or applications will discreetly bought to the attention of the Managing Director of ERG. Training and Cyber Security Education may be required as a follow project, or engaged prior to the completion of this project scope to enable a change process to be initiated.
Service Providers / Webhosts / Cloud Based Storage Providers / Applications | Secondary | Select Accurate records may not be available for log in information on web based platforms. | Log in data is to be the primary request and a secondary request for an authorised representative to engage with these providers as instructed.